# Xlink Inventory Management System

## Pilot Implementation Plan

Client: [Client Name]

Prepared By: 4D Analytics (Pty) Ltd

Document Version: 1.0

Date: December 2025

## Pilot Overview

Objective: Deploy and validate the Xlink Inventory Management System in a production environment over a 3-week period

Scope: Main warehouse operations with core user group (10-15 users)

Success Criteria:

Successful data migration from legacy systems with 99% accuracy

All core workflows operational and validated

User acceptance and positive feedback

Performance targets met (page load times, system uptime)

Clear operational benefits demonstrated

## The Four-Step Implementation Process

### Step 1: Device Registry Migration

Timeline: Days 1-3 (3 business days)

Source System: Microsoft Dynamics NAV

Objective: Extract complete device master data and migrate to Supabase PostgreSQL database

Activities:

Day 1: Access and Extraction

Obtain NAV system read-only access

Identify device master tables and related data structures

Export device data to CSV format

Document field mappings (NAV columns → Supabase schema)

Archive source data for validation

Day 2: Transformation and Cleansing

Remove duplicate records

Standardize formatting (SKU numbers, descriptions, categories)

Validate data integrity (required fields, foreign keys)

Apply business rules for categorization

Handle exceptions and edge cases

Day 3: Loading and Validation

Bulk import into Supabase Stock_Catalog table

Verify record counts match source

Test database queries and relationships

Validate data integrity constraints

Performance testing for query speed

Client Requirements:

NAV system access (read-only credentials)

IT contact available for system questions

Business rules documentation for device categorization

Approval for data extraction timing (off-peak hours if needed)

Deliverables:

Complete device registry in Supabase (all records migrated)

Data mapping documentation

Validation report with record counts and integrity checks

List of exceptions or data quality issues identified

### Step 2: Product Catalog Import

Timeline: Days 4-5 (2 business days)

Source System: SharePoint Lists

Objective: Import product catalog with pricing, categories, and supplier information

Activities:

Day 4: SharePoint Data Extraction

Access SharePoint site and identify product lists

Export product data (SKU, name, description, category, pricing)

Extract supplier information

Document product hierarchies and relationships

Export to structured format (CSV/JSON)

Day 5: Import and Configuration

Transform data to match Supabase schema

Import into Stock_Catalog and related tables

Link products to device registry

Configure stock level thresholds (min, max, reorder points)

Set up product categories and filters

Validate pricing and supplier data

Client Requirements:

SharePoint site URL and access permissions

List of SharePoint lists containing product data

Current categorization structure and taxonomy

Pricing structure and approval rules

Supplier contact information

Deliverables:

Searchable product catalog in system

Product-to-device linkage completed

Stock level thresholds configured per product

Category hierarchy established

Validation report

### Step 3: Technician Roster Integration

Timeline: Day 6 (1 business day)

Source System: HR System, Excel, or SharePoint

Objective: Load complete technician registry into Point of Presence (PoP) module

Activities:

Day 6: Roster Data Import

Collect technician roster data (name, ID, contact info, region)

Extract service area assignments

Gather GPS coordinates for common work locations (if available)

Import into PointofPresence table

Configure technician profiles:

Contact information (phone, email)

Region/territory assignments

Contractor IDs

Training status

Equipment assignments

Set up availability schedules

Define service boundaries and regions

Test technician lookup and assignment logic

Client Requirements:

Current technician list with complete contact information

Employee IDs or contractor numbers

Region/territory assignments

Service area definitions

Training completion records (if tracked)

Deliverables:

Complete technician registry in PoP module

Region-based assignment rules configured

Technician profiles accessible in dispatch workflow

GPS tracking enabled (if applicable)

Validation report

### Step 4: Stock Count Blitz

Timeline: Days 7-15 (5-7 business days + analysis)

Objective: Establish accurate baseline inventory levels for all stock items

Phase A: Preparation (Days 7-8)

Activities:

Schedule stock count during operational window

Divide warehouse into count zones

Assign zones to staff members

Create count sheets and labels

Configure count session in system

Train warehouse staff on mobile counting interface (2-hour session)

Brief supervisors on validation procedures

Training Agenda (2 hours):

System login and navigation

Mobile counting interface walkthrough

Serial number scanning and entry

Quantity adjustments

Handling discrepancies

Troubleshooting common issues

Q&A and hands-on practice

Phase B: Physical Count Execution (Days 9-11)

Activities:

Staff conduct physical count using tablets/smartphones

Enter counts directly into system via mobile interface

Real-time progress tracking via admin dashboard

Supervisor performs spot-checks and validation

Flag variances exceeding threshold for recount

Document any inventory issues discovered

Photograph damaged or questionable items

Count Best Practices:

Count zone-by-zone to minimize disruption

Two-person verification for high-value items

Separate count teams for serialized vs bulk items

Daily progress meetings to address issues

Real-time adjustment of staffing based on progress

Phase C: Reconciliation (Days 12-13)

Activities:

Compare physical counts against expected (from NAV)

Generate comprehensive variance report

Investigate significant discrepancies (>10% variance)

Conduct recounts where needed

Document root causes (theft, data entry errors, shrinkage, etc.)

Adjust stock levels to match physical reality

Classify inventory status:

In Stock (available for immediate dispatch)

Out of Stock (flagged for reorder/backorder)

Under Review (pending investigation)

Phase D: Analysis and Reporting (Days 14-15)

Activities:

Calculate overall inventory accuracy percentage

Identify fast-moving vs slow-moving items

Generate stock valuation report

Analyze variance trends by category/location

Develop reorder point recommendations

Create executive summary presentation

Document lessons learned and improvements

Client Requirements:

Warehouse access for training session (2 hours, one day)

2-3 warehouse staff for full week of counting

Supervisor availability for validation (2-3 hours daily)

Forklift or ladder access for high shelves

Tablets or smartphones for counting (provided by client or 4D)

Temporary hold on new orders during count (optional, recommended)

Deliverables:

Accurate baseline inventory in system (all items counted)

In Stock items ready for immediate ordering

Out of Stock items flagged for backorder workflow

Comprehensive variance report with root cause analysis

Inventory accuracy percentage by category

Reorder point recommendations by item

Stock valuation report

Executive summary presentation

## Pilot Timeline (Detailed Schedule)

### Week 1: Data Foundation

| Day | Activity | Deliverable | Client Involvement |
| --- | --- | --- | --- |
| 1 | NAV data extraction | Device data exported | IT access provided |
| 2 | Data transformation | Clean device data | Business rules clarification |
| 3 | Supabase data load | Device registry complete | Validation review |
| 4 | SharePoint extraction | Product data exported | SharePoint access granted |
| 5 | Product catalog import | Catalog complete | Category structure review |

### Week 2: Preparation and Count

| Day | Activity | Deliverable | Client Involvement |
| --- | --- | --- | --- |
| 6 | Technician roster import | PoP complete | Roster data provided |
| 7 | Training session | Staff trained | 3-4 staff attend (2 hrs) |
| 8 | Count preparation | Count zones assigned | Supervisor briefing |
| 9 | Physical count day 1 | Progress report | Counting team active |
| 10 | Physical count day 2 | Mid-count status | Counting team active |
| 11 | Physical count day 3 | Count completion | Supervisor spot-checks |
| 12 | Reconciliation | Variance report | Issue investigation |

### Week 3: Validation and Go-Live

| Day | Activity | Deliverable | Client Involvement |
| --- | --- | --- | --- |
| 13 | Analysis and reporting | Executive summary | Management review |
| 14 | System training (all users) | Training complete | All pilot users (2 hrs) |
| 15 | Live operations begin | First live orders | 10-15 users active |
| 16-18 | Pilot testing | Daily feedback | User testing |
| 19-21 | Evaluation | Decision recommendation | Management decision |

## Pilot Success Metrics

### Data Migration Quality

Target: 99%+ accuracy

Measurement:

Record count validation (source vs target)

Random sampling of 100 records for field-level accuracy

Query performance testing

Relationship integrity verification

Success Criteria:

All records migrated successfully

Zero critical data quality issues

Query response times <500ms

Foreign key relationships intact

### Stock Count Accuracy

Target: 95%+ accuracy

Measurement:

Physical count vs expected (NAV baseline)

Variance percentage by category

Number of recounts required

Root cause analysis of variances

Success Criteria:

Overall accuracy 95%+

High-value items 99%+ accuracy

Variances explainable with documented causes

Baseline established for future counts

### System Performance

Target: Sub-2-second page loads, 99.5%+ uptime

Measurement:

Lighthouse performance audits

Real user monitoring during pilot

API response time tracking

Uptime monitoring logs

Success Criteria:

Initial page load <2 seconds (95th percentile)

Subsequent navigation <500ms

API response <500ms (95th percentile)

Zero downtime during pilot period

### User Adoption

Target: 80%+ daily active usage

Measurement:

Daily active users tracking

Feature usage analytics

Login frequency

Task completion rates

Success Criteria:

80%+ of pilot users log in daily

Core workflows (order, pick, dispatch) used consistently

Minimal support tickets for basic operations

Users prefer new system over legacy

### User Satisfaction

Target: 4/5 average rating

Measurement:

Post-pilot survey (1-5 scale)

Qualitative feedback interviews

Feature request tracking

Pain point documentation

Success Criteria:

Average satisfaction 4/5 or higher

Majority prefer new system to PowerApps

Positive feedback on mobile experience

Actionable improvement suggestions documented

## Pilot Scope Definition

### Included Functionality

The following modules are fully operational during the pilot:

Stock Order Management

Order creation with multi-step wizard

Draft order saving

Business line conditional logic

Stock availability checking

Order submission and confirmation

Picking Queue and Cart

Pending order display

Order assignment to pickers

Serial number capture with validation

Duplicate detection

Progress tracking

Picking completion workflow

Dispatch Management

Dispatch queue with picked orders

Method selection (Collection, Delivery, Courier)

Waybill entry

PDF manifest generation

Dispatch completion and notifications

Point of Presence

Technician lookup

Contact information access

Location and region data

Assignment integration with dispatch

Inventory Visibility

Stock level viewing

Item search and filtering

In Stock / Out of Stock status

Basic reporting

Asset Tracking

Device lookup by serial number

Asset status viewing

Basic asset information

Xlink-Sage AI Assistant

Question answering

Navigation guidance

System help and training

### Limited During Pilot

The following features are available but may have reduced functionality:

Stock Counting

Mobile counting via web browser (not dedicated native app)

Basic count entry and variance tracking

Full cycle count scheduling available post-pilot

Advanced Reporting

Basic reports available

PowerBI dashboard active but with limited historical data

Full analytics expand after pilot period

Bulk Operations

Bulk actions available but may need refinement based on pilot feedback

### Excluded from Pilot

The following are not part of the pilot evaluation:

Business Central Integration

Not included in pilot

Can be evaluated separately if needed post-pilot

Native Mobile Apps

PWA (web app) used instead

Native apps can be developed if needed

Advanced Analytics

Beyond basic KPIs

Full analytics suite available post-pilot

Custom Hardware

Bluetooth scanners not required (camera-based scanning)

Can be integrated if needed

## Risk Assessment and Mitigation

### Risk 1: Data Quality Issues from Legacy Systems

Probability: Medium

Impact: High

Description:

NAV or SharePoint data contains duplicates, formatting inconsistencies, or missing values

Poor data quality delays migration or causes operational issues

Mitigation Strategy:

Conduct data quality audit in Week 1 Day 1

Build comprehensive data cleansing into migration process

Have 4D team available for real-time issue resolution

Keep source systems intact during pilot (parallel run capability)

Document all data quality issues for client remediation

Contingency:

If critical data quality issues identified, extend Week 1 by 2-3 days

Client IT team assists with source data cleanup

Implement data validation rules to prevent future issues

### Risk 2: User Resistance to New System

Probability: Medium

Impact: Medium

Description:

Users comfortable with PowerApps resist change

Adoption slower than expected

Training inadequate for user needs

Mitigation Strategy:

Involve users early in pilot design and feedback

Hands-on training with actual warehouse tasks (not just slides)

Xlink-Sage AI assistant provides in-app guidance

Quick wins demonstrated immediately (time savings, mobile access)

Collect daily feedback and iterate rapidly

Identify power users to champion adoption

Contingency:

Additional training sessions scheduled as needed

One-on-one coaching for struggling users

Gather specific feedback to address pain points

Consider extended pilot period if adoption is slow

### Risk 3: Stock Count Disrupts Operations

Probability: Low

Impact: Medium

Description:

Stock count interferes with normal warehouse operations

Count takes longer than expected

Staff unavailable during peak times

Mitigation Strategy:

Schedule count during slow operational period (coordinate with client)

Use zone-based counting (operations continue in other zones)

Allow full week for count completion (not rushed)

Leverage existing staff familiar with inventory

Supervisor monitors progress and adjusts staffing

Contingency:

Extend count period by 2-3 days if needed

Prioritize fast-moving items for initial count

Complete slow-moving items in second pass

Option to run partial operations during count

### Risk 4: Integration Challenges with NAV

Probability: Medium

Impact: Medium

Description:

NAV data extraction more complex than anticipated

Data structures undocumented

IT access delayed or restricted

Mitigation Strategy:

Start with read-only exports (low risk, no system impact)

Manual CSV export as fallback option

No live integration required for pilot (one-time export)

IT engagement early (Day 1) to resolve access issues

Document all NAV structures for future reference

Contingency:

Use manual exports if API access unavailable

Client IT assists with data extraction

Defer live integration discussion to post-pilot

### Risk 5: Infrastructure Downtime or Performance Issues

Probability: Low

Impact: High

Description:

Supabase or Netlify service outage during pilot

Performance does not meet targets

Network connectivity issues at warehouse

Mitigation Strategy:

Supabase and Netlify have 99.9% uptime SLAs

Multi-region redundancy built into infrastructure

PWA offline mode for critical operations (counts, picks)

4D team monitors system performance during pilot hours

Pre-pilot load testing to validate capacity

Contingency:

If critical outage occurs, pilot day is extended by 1 day

Offline capabilities minimize operational impact

4D team on call for immediate response

Rollback to PowerApps as backup (runs in parallel)

## Post-Pilot Decision Framework

### Go Decision (Proceed to Full Production)

Criteria:

Data migration successful with 99%+ accuracy

All core workflows operational and validated

User satisfaction rating 4/5 or higher

Performance metrics met (load time <2s, uptime 99.5%+)

Clear operational benefits demonstrated

Management approval obtained

Next Steps:

Finalize project agreement and payment schedule

Plan full rollout to remaining warehouses/users

Schedule additional training for new users

Establish ongoing support and maintenance plan

Define enhancement roadmap

### Go with Modifications (Conditional Proceed)

Criteria:

Core system works but minor issues identified

User requests for enhancements or workflow adjustments

Data quality needs refinement

Performance acceptable but could improve

Training approach needs adjustment

Next Steps:

Document all requested modifications

Provide fixed-price quotes for enhancements

Create prioritized backlog

Agree on timeline for modifications

Plan second validation phase after changes

### No-Go Decision (Do Not Proceed)

Criteria:

Critical functionality failures that cannot be resolved

Data integrity cannot be assured

User adoption below 50%

Performance unacceptable and not fixable within reasonable timeline

Management determines legacy system is superior

Next Steps:

Conduct root cause analysis of failure

Document lessons learned

Provide detailed report on issues

Propose remediation plan if client wants to revisit

Ensure clean separation (no obligations)

## Client Responsibilities

### IT Department

Week 1:

Provide NAV system access (read-only credentials)

Grant SharePoint site permissions

Confirm data export procedures and timing

Available for technical questions (estimated 2 hours total)

Review and validate migrated data

Week 2:

Provide technician roster data

Assist with any data quality issues

Support count preparation

Week 3:

Monitor system performance

Assist with user questions

Participate in evaluation

### Warehouse Team

Week 1:

Provide input on data accuracy

Review product catalog for completeness

Week 2:

Attend training session (2 hours, 3-4 staff)

Participate in stock count (full week, 3-4 staff)

Provide daily progress updates during count

Report any issues immediately

Week 3:

Participate in live pilot testing (10-15 users)

Provide daily feedback on system usage

Complete post-pilot survey

Assist with evaluation

### Management Team

Throughout Pilot:

Review weekly progress reports (30-minute calls)

Make Go/No-Go decision at end of Week 3

Communicate pilot purpose and objectives to staff

Authorize data access and staff time allocation

Remove organizational barriers

Week 3:

Attend final evaluation presentation

Provide decision within 3 business days of pilot completion

## 4D Analytics Deliverables

### Week 1: Foundation

Data migration scripts and transformation logic

Data validation reports (record counts, integrity checks)

System access credentials and configuration

Initial training documentation

### Week 2: Execution

Stock count training session (2 hours, in-person or virtual)

Real-time support during count (phone/email/chat)

Daily progress reports

Issue resolution and troubleshooting

### Week 3: Evaluation

Comprehensive pilot evaluation report

User feedback summary with quantitative and qualitative analysis

Performance metrics and benchmarks

Lessons learned and recommendations

Go-forward implementation plan (if proceeding)

Updated project plan with any modifications

## Communication Plan

### Weekly Status Meetings

Frequency: Every Friday at [agreed time]

Duration: 30 minutes

Attendees: Client project manager, warehouse supervisor, IT liaison, 4D project manager

Agenda:

Progress update (completed, in-progress, upcoming)

Issues and blockers

User feedback highlights

Metrics review

Next week priorities

### Daily Stand-ups (During Count Week Only)

Frequency: Every morning at [agreed time] during Days 9-13

Duration: 15 minutes

Attendees: Warehouse supervisor, 4D support lead

Agenda:

Yesterday's progress

Today's plan

Blockers or issues

### Ad-Hoc Communication

Support Channels:

Email: [4D Support Email] (response within 4 hours)

Phone: [4D Support Phone] (available 8 AM - 6 PM SAST)

WhatsApp/Teams: [Group or direct contact] for urgent issues

Ticketing System: [URL if applicable] for tracking

### Escalation Procedures

Standard Issues:

Report via email or ticket

Response within 4 hours (business hours)

Resolution target: 24 hours

Critical Issues (system down, data loss, security breach):

Immediate phone call to [4D Emergency Contact]

Acknowledgment within 1 hour

Resolution team mobilized immediately

Client management notified within 2 hours

## Pilot Costs and Commitments

### Included at No Additional Cost

The pilot evaluation is provided as part of the overall project with no separate pilot fee. All activities and deliverables listed in this plan are included.

Client Investment:

Staff time for training and participation

IT resources for data access

Warehouse access during count period

Management time for reviews and decision

4D Analytics Investment:

Data migration development and execution

Training session delivery

Pilot support (3 weeks, business hours)

Evaluation and reporting

Infrastructure costs during pilot

### Post-Pilot Commitments

If the client decides to proceed after successful pilot:

System Ownership:

One-time payment for completed system development

Transfer of source code and full IP rights

Ongoing infrastructure costs (Supabase, Netlify, etc.)

Optional Services:

Custom refinements (quoted separately as fixed-price projects)

Annual maintenance contract (15% of project value, includes enhancements)

Additional training for new users

Feature development roadmap

If No-Go Decision:

Zero financial obligation

Clean separation with no strings attached

All pilot data exportable to client

## Next Steps to Launch Pilot

### Step 1: Pilot Approval

Client reviews and approves this pilot plan

Identify specific pilot start date (Week 1, Day 1)

Confirm pilot team members:

Client project manager

IT liaison

Warehouse supervisor

3-4 warehouse staff for count

10-15 end users for Week 3 testing

### Step 2: Pre-Pilot Kickoff Meeting (1 week before start)

Agenda (1 hour):

Introduce all team members

Review pilot objectives and timeline

Confirm data access requirements

Set up communication channels (email, WhatsApp, Teams)

Share training materials in advance

Schedule all meetings (weekly status, training sessions)

Address questions and concerns

Confirm Week 1 Day 1 activities

### Step 3: Week 1 Execution

Day 1:

IT provides NAV access

4D team begins data extraction

First status update sent

Days 2-5:

Data migration continues

Daily email updates on progress

Client validates migrated data

### Step 4: Weekly Check-ins

Week 1: Data migration progress (30 minutes, Friday)

Week 2: Stock count progress (30 minutes, Friday)

Week 3: Pilot evaluation and decision (60 minutes, Friday)

## Success Indicators

At the end of the 3-week pilot, the following indicators will demonstrate success:

1. Data Integrity: All legacy data successfully migrated and validated

2. Operational Readiness: Core workflows functional and tested

3. User Confidence: Staff trained and comfortable using the system

4. Performance: System meets or exceeds speed and reliability targets

5. Business Value: Clear operational improvements documented

6. Stakeholder Buy-in: Management approval to proceed

## Appendices

### Appendix A: Training Session Outline

Session 1: Stock Counting (Day 7, 2 hours)

System overview and login (15 minutes)

Mobile counting interface (30 minutes)

Serial number scanning and entry (30 minutes)

Handling variances and recounts (15 minutes)

Troubleshooting and Q&A (30 minutes)

Session 2: Full System Training (Day 14, 2 hours)

Stock order creation (30 minutes)

Picking queue and cart (30 minutes)

Dispatch management (30 minutes)

Asset lookup and tracking (15 minutes)

Xlink-Sage AI assistant (15 minutes)

### Appendix B: Data Migration Checklist

NAV Data:

Device master table identified

Access credentials obtained

Data export completed

CSV format validated

Field mapping documented

Data cleansing completed

Supabase import successful

Record count validated

Query testing completed

SharePoint Data:

Product catalog lists identified

Access permissions granted

Data export completed

Product hierarchy documented

Pricing data validated

Category structure mapped

Supabase import successful

Product search tested

Technician Roster:

Roster data collected

Contact information validated

Region assignments confirmed

Import to PoP table completed

Technician lookup tested

### Appendix C: Stock Count Zone Assignment Template

| Zone | Location | Item Count | Assigned Staff | Estimated Hours | Status |
| --- | --- | --- | --- | --- | --- |
| A | Aisle 1-3 | 250 | [Name] | 4 | Pending |
| B | Aisle 4-6 | 300 | [Name] | 5 | Pending |
| C | Aisle 7-9 | 220 | [Name] | 4 | Pending |
| D | High-value secure | 100 | [Name] + Supervisor | 3 | Pending |
| E | Bulk storage | 180 | [Name] | 3 | Pending |

### Appendix D: Pilot Feedback Survey Template

User Satisfaction Survey (1-5 scale, 1=Poor, 5=Excellent)

1. Overall system usability:

2. Mobile interface experience:

3. System speed and performance:

4. Training adequacy:

5. Xlink-Sage AI assistant helpfulness:

6. Preference vs. PowerApps:

Open-Ended Questions:

1. What features did you find most useful?

2. What was most frustrating or difficult?

3. What improvements would you suggest?

4. Would you recommend adopting this system? Why or why not?

### Appendix E: Contact Information

4D Analytics Team:

Project Manager: [Name] | [Phone] | [Email]

Technical Lead: [Name] | [Phone] | [Email]

Support Hotline: [Phone] (8 AM - 6 PM SAST)

Emergency Contact: [Phone] (Critical issues only)

Client Team:

Project Manager: [Name] | [Phone] | [Email]

IT Liaison: [Name] | [Phone] | [Email]

Warehouse Supervisor: [Name] | [Phone] | [Email]

End of Pilot Implementation Plan

Prepared by: 4D Analytics (Pty) Ltd | Enterprise Number: 2018/420599/07